## Mapping
Alpha | Concern | Color | Definition | Description | Card | Checklist
Story Card - Prescriptive | Customer | Green | TBD | TBD
Named
Feature is not prioritized
Feature is briefly described
Ready to be Pointed
Feature is prioritized
Story describes clear acceptance criteria
Easy for PM to validate acceptance criteria
Story only describes user interaction with system
Story is as small as possible while still being a cohesive unit of work (ideal)
Story uses Gerkin to describe acceptance criteria (Ideal)
Business value is clear (ideal)
Estimated
Feature is estimated
Nothing blocks developers from working on the story (ideal)
Started
A pair of deveopers are actively working on the story (ideal)
Blocked
A depedency prevents developers from making forward progress on the story
Finished
Code is readable
Code is refactored to remove duplication
Unit tests pass
Acceptance tests pass
Continuous integration passes
Code reviewed prior to commit (e.g. pair programming or code review) (ideal)
Changes reviewed prior to commit (e.g. git add -p)
Delivered
Feature is deployed to acceptance environment
Accepted
PM accepts story as done
Rejected
The delivered story does not match the acceptance criteria of the story (or)
The PM updated the acceptance criteria because they were not clear
Story Card - Descriptive | Customer | Green | TBD | TBD
Named
Feature is not prioritized
Feature is briefly described
Ready to be Pointed
Feature is prioritized
Story describes clear acceptance criteria
Easy for PM to validate acceptance criteria
Story only describes user interaction with system
Estimated
Feature is estimated
Started
A developer or pair of deveopers are actively working on the story
Blocked
A depedency prevents developers from making forward progress on the story
Finished
Code is readable
Code is refactored to remove duplication
Unit tests pass
Acceptance tests pass
Continuous integration passes
Code reviewed prior to commit
Changes reviewed prior to commit
Delivered
Feature is deployed to acceptance environment
Accepted
PM accepts story as done
Rejected
The delivered story does not match the acceptance criteria of the story (or)
The PM updated the acceptance criteria because they were not clear (or)
The PM added additional requirements that need to be implemented (or)
The PM changed the requirements and the code needs rework (or)
The PM updated the acceptance criteria because of conflicting requirements (or)
The QA manager added new requirements