## Mapping
Alpha | Concern | Color | Definition | Description | Card | Checklist
Stakeholders | Customer | Green | The people, groups, or organizations who affect or are affected by a software system. | The stakeholders provide the opportunity, and are the source of the requirements for the software system. They are involved throughout the software engineering endeavor to support the team and ensure that an acceptable software system is produced.
Recognized
Stakeholders have been identified
There is agreement on stakeholder groups to be represented
Responsibilities of stakeholder representatives defined
Represented
Stakeholder representatives appointed
Stakeholder representatives agreed to take on responsibilities & authorized
Collaboration approach agreed
Representatives respect team way of working
Involved
Stakeholder representatives carry out responsibilities
Stakeholder representatives provide feedback & take part in decisions in timely way
Stakeholder representatives promptly communicate to stakeholder group
In Agreement
Stakeholder representatives agree their input is valued and respected by the team
Stakeholder representatives agree with priorities
Stakeholder representatives have agreed upon minimal expectations for deployment
Satisfied for Deployment
Stakeholder representatives provide feedback on system from their stakeholder group perspective
Stakeholder representatives confirm system ready for deployment
Satisfied in Use
System has met or exceed minimal stakeholder expectations
Stakeholder needs and expectations are being met
Opportunity | Customer | Green | The set of circumstances that makes it appropriate to develop or change a software system. | The opportunity articulates the reason for the creation of the new, or changed, software system. It represents the team’s shared understanding of the stakeholders’ needs, and helps shape the requirements for the new software system by providing justification for its development.
Identified
Opportunity identified that could be addressed by a software-based solution
A stakeholder wishes to make an investment in better understanding potential value
Other stakeholders who share opportunity identified
Solution Needed
Need for software-based solution confirmed
Stakeholders needs identified
Underlying problem and root causes identified
At least 1 software-based solution proposed
Value Established
The value of a successful solution established
Impact of solution on stakeholders understood
Value of software system understood
Viable
A solution has been outlined
Indications are solution can be developed & deployed within constraints
Risks are manageable
Addressed
A solution has been produced that demonstrably addresses opportunity
A usable system is available
Stakeholders agree worth deploying
Stakeholders satisfied solution addresses opportunity
Benefit Accrued
Operational use creating tangible benefits
Return on investment profile at least as good as anticipated
Requirements | Solution | Yellow | This area of concern covers everything to do with the specification and development of the software system. | The goal of software engineering is to develop working software as part of the solution to some problem. Any method adopted must describe a set of practices to help the team produce good quality software in a productive and collaborative fashion.
Conceived
The need for a new system is clear
Users are identified
Initial sponsors are identified
Bounded
The purpose and extent of the system are agreed
Success criteria are clear
Mechanisms for handling requirements are agreed
Constraints and assumptions identified
Coherent
The big picture is clear and shared by all involved
Important usage scenarios explained
Priorities are clear
Conflicts are addressed
Impact is understood
Acceptable
Requirements describe a solution acceptable to the stakeholders
The rate of change to agreed requirements is low
Value is clear
Addressed
Enough requirements are implemented for the system to be acceptable
Stakeholders agree the system is worth making operational
Fulfilled
The system fully satisfies the requirements and the need
There are no outstanding requirements items preventing completion
Software System | Solution | Yellow | A system made up of software, hardware, and data that provides its primary value by the execution of the software. | A software system can be part of a larger software, hardware, business or social solution.
Architecture Selected
Architecture selected that address key technical risks
Criteria for selecting architecture agreed
Platforms, technologies, languages selected
Buy, build, reuse decisions made
Demonstrable
Key architecture characteristics demonstrated
Relevant stakeholders agree architecture is appropriate
Critical interface and system configurations exercised
Usable
System is usable and has desired quality characteristics
System can be operated by users
Functionality and performance have been tested and accepted
Defect levels acceptable
Release content known
Ready
User documentation available
Stakeholder representatives accept system
Stakeholder representatives want to make system operational
Operational
System in use in operational environment
System available to intended users
At least one example of system is fully operational
System supported to agreed service levels
Retired
System no longer supported
Updates to system will no longer be produced
System has been replaced or discontinued
Team | Endeavor | Blue | The group of people actively engaged in the development, maintenance, delivery and support of a specific software system. | The team plans and performs the work needed to create, update and/or change the software system.
Seeded
Team's mission is clear
Team knows how to grow to achieve mission
Required competencies are identified
Team size is determined
Formed
Team has enough resources to start the mission
Team organization & individual responsibilities understood
Members know how to perform work
Collaborating
Members working as one unit
Communication is open and honest
Members focused on team mission
Success of team ahead of personal objectives
Performing
Team working efficiently and effectively
Adapts to changing context
Produce high quality output
Minimal backtracking and re-work
Waste continually eliminated
Adjourned
Team no longer accountable
Responsibilities handed over
Members available for other assignment
Way-of-Working | Endeavor | Blue | The tailored set of practices and tools used by a team to guide and support their work. | The team evolves their way of working alongside their understanding of their mission and their working environment. As their work proceeds they continually reflect on their way of working and adapt it to their current context, if necessary.
Principles Established
Principles and constraints established
Principles and constraints committed to
Practices and tools agreed to
Context team operates in understood
Foundation Established
Key practices and tools ready
Gaps that exist between practices and tools analyzed and understood
Capability gaps analyzed and understood
Selected practices, and tools integrated
In Use
Some members of the team are using the way of working
Use of practices and tools regularly inspected
Practices and tools being adapted and supported by team
Procedures in place to handle feedback
In Place
All members of the team are using the way of working
All members have access to practices and tools to do their work
Whole team involved in inspection and adaptation of way of working
Working well
Way of working is working well for team
Team members are making progress as planned
Team naturally applies practices without thinking about them
Tools naturally support way of working
Retired
Way of working no longer in use by team
Lessons learnfuture use
Work | Endeavor | Blue | Activity involving mental or physical effort done in order to achieve a result. | In the context of software engineering, work is everything that the team does to meet the goals of producing a software system matching the requirement and addressing the opportunity presented by the stakeholders. The work is guided by the practices that make up the team’s way-of-working.
Initiated
Work initiator known
Work constraints clear
Sponsorship and funding model clear
Priority of work clear
Prepared
Cost & effort estimated
Funding and resources to start work in place
Acceptance criteria understood
Governance procedures agreed
Risk exposure understood
Dependencies clear
Started
Development work has started
Work progress is monitored
Work broken down into actionable items with clear definition of done
Team members are accepting and progressing work items
Under Control
Work going well, risks being managed
Unplanned work & re-work under control
Work items completed within estimates
Measures tracked
Concluded
Work to produce results have been finished
Work results are being achieved
The client has accepted the resulting software system
Closed
All remaining housekeeping tasks completed, and work officially closed
Everything has been archived
Lessons learned and metrics made available