## Mapping
Alpha | Concern | Color | Definition | Description | Card | Checklist | Corresponding item in the card/strip
Stakeholders | Customer | Green | The people, groups, or organizations who affect or are affected by a software system. | The stakeholders provide the opportunity, and are the source of the requirements for the software system. They are involved throughout the software engineering endeavor to support the team and ensure that an acceptable software system is produced.
Recognized
[6 empty] | All the different groups of stakeholders that are, or will be, affected by the development and operation of the software system are identified. | stakeholders have been identified
[6 empty] | There is agreement on the stakeholder groups to be represented. At a minimum, the stakeholders groups that fund, use, support, and maintain the system have been considered. | there is an agreement for stakeholder groups to be represented
[6 empty] | The responsibilities of the stakeholder representatives have been defined. | responsibilities of stakeholder representatives defined
Represented
[6 empty] | The stakeholder representatives have agreed to take on their responsibilities. | stakeholder representatives appointed
[6 empty] | The stakeholder representatives are authorized to carry out their responsibilities. | stakeholder representatives agreed to take on responsibilities & authorized
[6 empty] | The collaboration approach among the stakeholder representatives has been agreed. | collaboration approach agreed
[6 empty] | The stakeholder representatives support and respect the team's way of working. | representatives respect team way of working
Involved
[6 empty] | The stakeholder representatives assist the team in accordance with their responsibilities. | stakeholder representatives carry out responsibilities
[6 empty] | The stakeholder representatives provide feedback and take part in decision making in a timely manner. | stakeholder representatives provide feedback & take part in decisions in timely way
[6 empty] | The stakeholder representatives promptly communicate changes that are relevant for their stakeholder groups. | stakeholder representatives promptly communicate to stakeholder group
In Agreement
[6 empty] | The stakeholder representatives have agreed upon their minimal expectations for the next deployment of the new system. | stakeholder representative agree their input is valued & respected by the team
[6 empty] | The stakeholder representatives are happy with their involvement in the work. | stakeholder representative agree with priorities
[6 empty] | The stakeholder representatives agree that their input is valued by the team and treated with respect. | stakeholder representatives agreed upon minimal expectations for deployment
The stakeholder representatives agree with how their different priorities and perspectives are being balanced to provide a clear direction for the team.
Satisfied for Deployment
[6 empty] | The stakeholder representatives provide feedback on the system from their stakeholder group perspective. | stakeholder representatives provide feedback on system from their stakeholder perspective
[6 empty] | The stakeholder representatives confirm that the system is ready for deployment. | stakeholder representatives confirm system ready for deployment
Satisfied in Use
[6 empty] | Stakeholders are using the new system and providing feedback on their experiences. | system has met or exceeded minimum stakeholder expectations
[6 empty] | The stakeholders confirm that the new system meets their expectations. | stakeholder need and expectations are being met
Opportunity | Customer | Green | The set of circumstances that makes it appropriate to develop or change a software system. | The opportunity articulates the reason for the creation of the new, or changed, software system. It represents the team’s shared understanding of the stakeholders’ needs, and helps shape the requirements for the new software system by providing justification for its development.
Identified
[6 empty] | An idea for a way of improving current ways of working, increasing market share or applying a new or innovative software system has been identified. | opportunity identified that could be addressed by a software-based solution
[6 empty] | At least one of the stakeholders wishes to make an investment in better understanding the opportunity and the value associated with addressing it. | a stakeholder wishes to make an investment in better understanding potential value
[6 empty] | The other stakeholders who share the opportunity have been identified. | other stakeholders who share opportunity identified
Solution Needed
[6 empty] | The stakeholders in the opportunity and the proposed solution have been identified. | need for software-based solution confirmed
[6 empty] | The stakeholders' needs that generate the opportunity have been established. | stakeholder needs identified
[6 empty] | Any underlying problems and their root causes have been identified. | underlying problem and root causes identified
[6 empty] | It has been confirmed that a software-based solution is needed. | at least 1 software-based solution proposed
At least one software-based solution has been proposed.
Value Established
[6 empty] | The value of addressing the opportunity has been quantified either in absolute terms or in returns or savings per time period (e.g. per annum). | the value of a successful solution established
[6 empty] | The impact of the solution on the stakeholders is understood. | impact of solution on stakeholders understood
[6 empty] | The value that the software system offers to the stakeholders that fund and use the software system is understood. | value of software system understood
The success criteria by which the deployment of the software system is to be judged are clear.
The desired outcomes required of the solution are clear and quantified.
Viable
[6 empty] | A solution has been outlined. | a solution has been identified
[6 empty] | The indications are that the solution can be developed and deployed within constraints. | indications are solutions can be developed & deployed within constraints
[6 empty] | The risks associated with the solution are acceptable and manageable. | risks are manageable
The indicative (ball-park) costs of the solution are less than the anticipated value of the opportunity.
The reasons for the development of a software-based solution are understood by all members of the team
It is clear that the pursuit of the opportunity is viable.
Addressed
[6 empty] | A usable system that demonstrably addresses the opportunity is available. | a solution has been produced that demonstrably addresses opportunity
[6 empty] | The stakeholders agree that the available solution is worth deploying. | a usable system is available
[6 empty] | The stakeholders are satisfied that the solution produced addresses the opportunity. | stakeholders agree worth deploying
stakeholders satisfied solution addresses opportunity
Benefit Accrued
[6 empty] | The solution has started to accrue benefits for the stakeholders. | operational use creating tangible benefits
[6 empty] | The return-on-investment profile is at least as good as anticipated. | return on investment profile at least as good as anticipated
Requirements | Solution | Yellow | This area of concern covers everything to do with the specification and development of the software system. | The goal of software engineering is to develop working software as part of the solution to some problem. Any method adopted must describe a set of practices to help the team produce good quality software in a productive and collaborative fashion.
Conceived
[6 empty] | The initial set of stakeholders agrees that a system is to be produced. | the need for a new system is clear
[6 empty] | The stakeholders that will use the new system are identified. | users are identified
[6 empty] | The stakeholders that will fund the initial work on the new system are identified. | initial sponsors are identified
There is a clear opportunity for the new system to address.
Bounded
[6 empty] | The stakeholders involved in developing the new system are identified. | the purpose and extent of the system are agreed
[6 empty] | The stakeholders agree on the purpose of the new system. | success criteria are clear
[6 empty] | It is clear what success is for the new system. | mechanisms for handling requirements are in place
[6 empty] | The stakeholders have a shared understanding of the extent of the proposed solution. | constraints and assumptions are identified
The way the requirements will be described is agreed upon.
The mechanisms for managing the requirements are in place.
The prioritization scheme is clear.
Constraints are identified and considered.
Assumptions are clearly stated.
Coherent
[6 empty] | The requirements are captured and shared with the team and the stakeholders. | the big picture is clear and shared by all involved
[6 empty] | The origin of the requirements is clear. | important usage scenarios explained
[6 empty] | The rationale behind the requirements is clear. | priorities are clear
[6 empty] | Conflicting requirements are identified and attended to. | conflicts are addressed
[6 empty] | The requirements communicate the essential characteristics of the system to be delivered. | impact is understood
The most important usage scenarios for the system can be explained.
The priority of the requirements is clear.
The impact of implementing the requirements is understood.
The team understands what has to be delivered and agrees to deliver it.
Acceptable
[6 empty] | The stakeholders accept that the requirements describe an acceptable solution. | requirements describe a solution acceptable to the stakeholders
[6 empty] | The rate of change to the agreed requirements is relatively low and under control. | the rate of change to agreed requirements is low
[6 empty] | The value provided by implementing the requirements is clear. | value is clear
The parts of the opportunity satisfied by the requirements are clear.
Addressed
[6 empty] | Enough of the requirements are addressed for the resulting system to be acceptable to the stakeholders. | enough requirements are implemented for the system to be acceptable
[6 empty] | The stakeholders accept the requirements as accurately reflecting what the system does and does not do. | stakeholders agree the system is worth making operational
The set of requirement items implemented provide clear value to the stakeholders.
The system implementing the requirements is accepted by the stakeholders as worth making operational.
Fulfilled
[6 empty] | The stakeholders accept the requirements as accurately capturing what they require to fully satisfy the need for a new system. | the system fully satisfies the requirements and the need
[6 empty] | There are no outstanding requirement items preventing the system from being accepted as fully satisfying the requirements. | there are no outstanding requirements items preventing completion
The system is accepted by the stakeholders as fully satisfying the requirements.
Software System | Solution | Yellow | A system made up of software, hardware, and data that provides its primary value by the execution of the software. | A software system can be part of a larger software, hardware, business or social solution.
Architecture Selected
[6 empty] | The criteria to be used when selecting the architecture have been agreed on. | Architecture selected that address key technical risks
[6 empty] | Hardware platforms have been identified. | criteria for selecting architecture agreed
[6 empty] | Programming languages and technologies to be used have been selected. | platforms, technologies, languages selected
[6 empty] | System boundary is known. | buy, build, reuse decisions made
Significant decisions about the organization of the system have been made.
Buy, build and reuse decisions have been made.
Demonstrable
[6 empty] | Key architectural characteristics have been demonstrated. | key architecture characteristics demonstrated
[6 empty] | The system can be exercised and its performance can be measured. | relevant stakeholders agree architecture is appropriate
[6 empty] | Critical hardware configurations have been demonstrated. | critical interface and system configurations exercised
Critical interfaces have been demonstrated.
The integration with other existing systems has been demonstrated.
The relevant stakeholders agree that the demonstrated architecture is appropriate.
Usable
[6 empty] | The system can be operated by stakeholders who use it. | system is usable and has desired quality characteristics
[6 empty] | The functionality provided by the system has been tested. | system can be operated by users
[6 empty] | The performance of the system is acceptable to the stakeholders. | functionality and performance have been tested and accepted
[6 empty] | Defect levels are acceptable to the stakeholders. | defect levels acceptable
[6 empty] | The system is fully documented. | release content known
Release content is known.
The added value provided by the system is clear.
Ready
[6 empty] | Installation and other user documentation are available. | user documentation available
[6 empty] | The stakeholder representatives accept the system as fit-for-purpose. | stakeholder representatives accept system
[6 empty] | The stakeholder representatives want to make the system operational. | stakeholder representatives want to make system operational
Operational support is in place.
Operational
[6 empty] | The system has been made available to the stakeholders intended to use it. | system in use in operational environment
[6 empty] | At least one example of the system is fully operational. | system available to intended users
[6 empty] | The system is fully supported to the agreed service levels. | at least one example of system is fully operational
system supported to agreed service levels
Retired
[6 empty] | The system has been replaced or discontinued. | system no longer supported
[6 empty] | The system is no longer supported. | updates to system will no longer be produced
[6 empty] | There are no “official” stakeholders who still use the system. | system has been replaced or discontinued
Updates to the system will no longer be produced.
Team | Endeavor | Blue | The group of people actively engaged in the development, maintenance, delivery and support of a specific software system. | The team plans and performs the work needed to create, update and/or change the software system.
Seeded
[6 empty] | The team mission has been defined in terms of the opportunities and outcomes. | team's mission is clear
[6 empty] | Constraints on the team's operation are known. | team knows how to grow to achieve mission
[6 empty] | Mechanisms to grow the team are in place. | required competencies are identified
[6 empty] | The composition of the team is defined. | team size is determined
Any constraints on where and how the work is carried out are defined.
The team's responsibilities are outlined.
The level of team commitment is clear.
Required competencies are identified.
The team size is determined.
Governance rules are defined.
Leadership model is selected.
Formed
[6 empty] | Individual responsibilities are understood. | team has enough resources to start the mission
[6 empty] | Enough team members have been recruited to enable the work to progress. | team organization & individual responsibilities understood
[6 empty] | Every team member understands how the team is organized. | members know how to perform work
All team members understand how to perform their work.
The team members have met (perhaps virtually) and are beginning to get to know each other
The team members understand their responsibilities and how they align with their competencies.
Team members are accepting work.
Any external collaborators (organizations, teams and individuals) are identified.
Team communication mechanisms have been defined.
Each team member commits to working on the team as defined.
Collaborating
[6 empty] | The team is working as one cohesive unit. | members working as one unit
[6 empty] | Communication within the team is open and honest. | communication is open and honest
[6 empty] | The team is focused on achieving the team mission. | members focused on team mission
[6 empty] | The team members put the success of the team as a whole ahead of their own personal objectives. | success of team ahead of personal objectives
The team members know each other.
Performing
[6 empty] | The team consistently meets its commitments. | team working efficiently and effectively
[6 empty] | The team continuously adapts to the changing context. | adapts to changing context
[6 empty] | The team identifies and addresses problems without outside help. | produce high-quality output
[6 empty] | Effective progress is being achieved with minimal avoidable backtracking and reworking. | minimal backtracking and re-work
[6 empty] | The team is consistently producing high quality output. | waste continually eliminated
The team is considered a high performance team.
Effective progress is being achieved with minimal avoidable backtracking and reworking.
Wasted work, and the potential for wasted work are continuously eliminated.
Adjourned
[6 empty] | The team responsibilities have been handed over or fulfilled. | team no longer accountable
[6 empty] | The team members are available for assignment to other teams. | responsibilities handed over
[6 empty] | No further effort is being put in by the team to complete the mission. | members available for other assignment
Way-of-Working | Endeavor | Blue | The tailored set of practices and tools used by a team to guide and support their work. | The team evolves their way of working alongside their understanding of their mission and their working environment. As their work proceeds they continually reflect on their way of working and adapt it to their current context, if necessary. |  |  | THE STRIP REFLECTS A VERY UPFRONT VIEW OF SELECTING TOOLS & PRACTICES...
[5 empty] | Principles Established |  | The term principle is a bit vague. This state could be called "Agreed" ???
[6 empty] | Principles and constraints are committed to by the team. | principles and constraints established
[6 empty] | Principles and constraints are agreed to by the stakeholders. | principles and constraints committed to
[6 empty] | The practice needs of the work and its stakeholders are agreed. | practices and tools agreed to
[6 empty] | The tool needs of the work and its stakeholders are agreed. | context team operates in understood
A recommendation for the approach to be taken is available.
The context within which the team will operate is understood.
The constraints that apply to the selection and use of practices and tools are known.
The constraints that govern the selection and acquisition of the team's practices and tools are known.
[5 empty] | Foundation Established |  | The term foundation is a bit vague. This state could be called "In Place" or "Ready" ???
[6 empty] | The key practices and tools that form the foundation of the way-of-working are selected. | key practices and tools ready
[6 empty] | Enough practices for work to start are agreed to by the team. | gaps that exist between practices and tools analyzed and understood
[6 empty] | All non-negotiable practices and tools have been identified. | capability gaps analyzed and understood
[6 empty] | The gaps that exist between the practices and tools that are needed and the practices and tools that are available have been analyzed and understood. | selected practices, and tools integrated
The capability gaps that exist between what is needed to execute the desired way of working and the capability levels of the team have been analyzed and understood.
The selected practices and tools have been integrated to form a usable way-of-working.
In Use
[6 empty] | The practices and tools are being used to do real work. | some members of the team are using the way of working
[6 empty] | The use of the practices and tools selected is regularly inspected. | use of practices and tools regularly inspected
[6 empty] | The practices and tools are being adapted to the team’s context. | practices and tools being adapted and supported by the team
[6 empty] | The use of the practices and tools is supported by the team. | procedures in place to handle feedback
Procedures are in place to handle feedback on the team’s way of working.
The practices and tools support team working and collaboration.
In Place
[6 empty] | The practices and tools are being used by the whole team to perform their work. | all members of the team are using the way of working
[6 empty] | All team members have access to the practices and tools required to do their work. | all members have access to the practices and tools to do their work
[6 empty] | The whole team is involved in the inspection and adaptation of the way-of-working. | whole team involved in inspections and adaptation of way of working
Working well
[6 empty] | Team members are making progress as planned by using and adapting the way-of-working to suit their current context. | way of working is working well for team
[6 empty] | The team naturally applies the practices without thinking about them | team members are making progress as planned
[6 empty] | The tools naturally support the way that the team works. | team naturally applies practices without thinking about them
[6 empty] | The team continually tunes their use of the practices and tools. | tools naturally support the way of working
Retired
[6 empty] | The team's way of working is no longer being used. | way of working no longer in use by team
[6 empty] | Lessons learned are shared for future use. | lessons learned are shared for future use
Work | Endeavor | Blue | Activity involving mental or physical effort done in order to achieve a result. | In the context of software engineering, work is everything that the team does to meet the goals of producing a software system matching the requirement and addressing the opportunity presented by the stakeholders. The work is guided by the practices that make up the team’s way-of-working.
Initiated
[6 empty] | The result required of the work being initiated is clear. | work initiator known
[6 empty] | Any constraints on the work’s performance are clearly identified. | work constraints clear
[6 empty] | The stakeholders that will fund the work are known. | sponsorship and funding model clear
[6 empty] | The initiator of the work is clearly identified. | priority of work clear
The stakeholders that will accept the results are known.
The source of funding is clear.
The priority of the work is clear.
Prepared
[6 empty] | Commitment is made. | cost & effort estimated
[6 empty] | Cost and effort of the work are estimated. | funding and resources to start work in place
[6 empty] | Resource availability is understood. | acceptable criteria understood
[6 empty] | Governance policies and procedures are clear. | governance procedures agreed
[6 empty] | Risk exposure is understood. | risk exposure understood
[6 empty] | Acceptance criteria are defined and agreed with client. | dependencies clear
The work is broken down sufficiently for productive work to start.
Work items have been identified and prioritized by the team and stakeholders.
A credible plan is in place.
Funding to start the work is in place.
The team is ready to start the work.
Integration and delivery points are defined.
Started
[6 empty] | Development work has been started. | development work has started
[6 empty] | Work progress is monitored. | work progress is monitored
[6 empty] | The work is being broken down into actionable work items with clear definitions of done. | work broken down into actionable items with clear definition of done
[6 empty] | Team members are accepting and progressing work items. | team members accepting and progressing work items
Under Control
[6 empty] | Work items are being completed. | work going well, risks being managed
[6 empty] | Unplanned work is under control. | unplanned work & re-work under control
[6 empty] | Risks are under control as the impact if they occur and the likelihood of them occurring have been reduced to acceptable levels. | work items completed with estimates
[6 empty] | Estimates are revised to reflect the team’s performance. | measures tracked
Measures are available to show progress and velocity.
Re-work is under control.
Work items are consistently completed on time and within their estimates.
Concluded
[6 empty] | All outstanding work items are administrative housekeeping or related to preparing the next piece of work. | work to produce results have been finished
[6 empty] | Work results are being achieved. | work results are being achieved
[6 empty] | The client has accepted the resulting software system. | the client has accepted the resulting software system
Closed
[6 empty] | Lessons learned have been itemized, recorded and discussed. | all remaining housekeeping tasks completed, and work officially closed
[6 empty] | Metrics have been made available. | everything has been archived
[6 empty] | Everything has been archived. | lessons learned and metrics made available
The budget has been reconciled and closed.
The team has been released.
There are no outstanding, uncompleted work items.