## Mapping
Alpha | Concern | Color | Definition | Description | Card | Checklist | Corresponding item in the card/strip
Stakeholders | Customer | Green | The people, groups, or organizations who affect or are affected by a software system. | The stakeholders provide the opportunity, and are the source of the requirements for the software system. They are involved throughout the software engineering endeavor to support the team and ensure that an acceptable software system is produced.
Recoginzed
[6 empty] | All the different groups of stakeholders that are, or will be, affected by the development and operation of the software system are identified. | stakeholders have been identfied
[6 empty] | There is agreement on the stakeholder groups to be represented. At a minimum, the stakeholders groups that fund, use, support, and maintain the system have been considered. | there is an agreement for stakeholder groups to be represented
[6 empty] | The responsibilities of the stakeholder representatives have been defined. | responsibilites of stakeholder representatives defined
Represented
[6 empty] | Stakeholder representatives appointed. | stakeholder representatives appointed
[6 empty] | The stakeholder representatives have agreed to take on their responsibilities. | stakeholder representatives agreed to take on responsibilities & authorized
[6 empty] | The collaboration approach among the stakeholder representatives has been agreed. | collaboration approach agreed
[6 empty] | The stakeholder representatives support and respect the team's way of working. | representatives respect team way of working
The stakeholder representatives are authorized to carry out their responsibilities.
Involved
[6 empty] | The stakeholder representatives assist the team in accordance with their responsibilities. | stakeholder representatives carry out responsibilities
[6 empty] | The stakeholder representatives provide feedback and take part in decision making in a timely manner. | stakeholder representatives provide feedback & take part in decisions in timely way
[6 empty] | The stakeholder representatives promptly communicate changes that are relevant for their stakeholder groups. | stakeholder representatives promptly communicate to stakeholder group
In Agreement
[6 empty] | The stakeholder representatives agree that their input is valued by the team and treated with respect. | stakeholder representative agree their input is valued & respected by the team
[6 empty] | Stakeholder agree with prioritites | stakeholder representative agree with priorities
[6 empty] | The stakeholder representatives have agreed upon their minimal expectations for the next deployment of the new system. | stakeholder representatives agreed upon minimal expectations for deployment
The team members agree that their input is valued by the stakeholder representatives and treated with respect.
The stakeholder representatives agree with how their different priorities and perspectives are being balanced to provide a clear direction for the team.
The stakeholder representatives are happy with their involvement in the work.
Satisfied for Deployment
[6 empty] | The stakeholder representatives provide feedback on the system from their stakeholder group perspective. | stakeholder representatives provide feedback on system from their stakeholder perspective
[6 empty] | The stakeholder representatives confirm that the system is ready for deployment. | stakeholder representatives confirm system ready for deployment
Satisfied in Use
[6 empty] | System has met or exceeded minimal stakeholder expectations | system has met or exceeded minimum stakeholder expectations
[6 empty] | The stakeholders confirm that the new system meets their expectations. | stakeholder need and expectations are being met
Stakeholders are using the new system and providing feedback on their experiences.
Opportunity | Customer | Green | The set of circumstances that makes it appropriate to develop or change a software system. | The opportunity articulates the reason for the creation of the new, or changed, software system. It represents the team’s shared understanding of the stakeholders’ needs, and helps shape the requirements for the new software system by providing justification for its development.
Identified
[6 empty] | An idea for a way of improving current ways of working, increasing market share or applying a new or innovative software system has been identified. | opportunity identified that could be addressed by a software-based solution
[6 empty] | At least one of the stakeholders wishes to make an investment in better understanding the opportunity and the value associated with addressing it. | a stakeholder wishes to make an investment in better understanding potential value
[6 empty] | The other stakeholders who share the opportunity have been identified. | other stakeholders who share opportunity identified
Solution Needed
[6 empty] | It has been confirmed that a software-based solution is needed. | need for software-based solution confirmed
[6 empty] | The stakeholders' needs that generate the opportunity have been established. | stakeholder needs identified
[6 empty] | Any underlying problems and their root causes have been identified. | underlying problem and root causes identified
[6 empty] | At least one software-based solution has been proposed. | at least 1 software-based solution proposed
The stakeholders in the opportunity and the proposed solution have been identified.
Value Established
[6 empty] | The value of addressing the opportunity has been quantified either in absolute terms or in returns or savings per time period (e.g. per annum). | the value of a successful solution established
[6 empty] | The impact of the solution on the stakeholders is understood. | impact of solution on stakeholders understood
[6 empty] | The value that the software system offers to the stakeholders that fund and use the software system is understood. | value of software system understood
The success criteria by which the deployment of the software system is to be judged are clear.
The desired outcomes required of the solution are clear and quantified.
Viable
[6 empty] | A solution has been outlined. | a solution has been identified
[6 empty] | The indications are that the solution can be developed and deployed within constraints. | indications are solutions can be developed & deployed within constraints
[6 empty] | The risks associated with the solution are acceptable and manageable. | risks are manageable
The indicative (ball-park) costs of the solution are less than the anticipated value of the opportunity.
The reasons for the development of a software-based solution are understood by all members of the team.
It is clear that the pursuit of the opportunity is viable.
Addressed
[6 empty] | A usable system that demonstrably addresses the opportunity is available. | a solution has been produced that demonstrably addresses opportunity
[6 empty] | A usable system that demonstrably addresses the opportunity is available. | a usable system is available
[6 empty] | The stakeholders agree that the available solution is worth deploying. | stakeholders agree worth deploying
[6 empty] | The stakeholders are satisfied that the solution produced addresses the opportunity. | stakeholders satisfied solution adresses opportunity
Benefit Accrued
[6 empty] | The solution has started to accrue benefits for the stakeholders. | operational use creating tangible benefits
[6 empty] | The return-on-investment profile is at least as good as anticipated. | return on investment profile at least as good as anticipated
Requirements | Solution | Yellow | This area of concern covers everything to do with the specification and development of the software system. | The goal of software engineering is to develop working software as part of the solution to some problem. Any method adopted must describe a set of practices to help the team produce good quality software in a productive and collaborative fashion.
Conceived
[6 empty] | There is a clear opportunity for the new system to address. | the need for a new system is clear
[6 empty] | The stakeholders that will use the new system are identified. | users are identified
[6 empty] | The stakeholders that will fund the initial work on the new system are identified. | initial sponsors are identified
The initial set of stakeholders agrees that a system is to be produced.
Bounded
[6 empty] | The stakeholders agree on the purpose of the new system. | the purpose and extent of the system are agreed
[6 empty] | It is clear what success is for the new system. | success criteria are clear
[6 empty] | The mechanisms for managing the requirements are in place. | mechanisms for handling requirements are in place
[6 empty] | Constraints are identified and considered. | constraints and assumptions are identified
Assumptions are clearly stated.
The stakeholders have a shared understanding of the extent of the proposed solution.
The way the requirements will be described is agreed upon.
The prioritization scheme is clear.
The stakeholders involved in developing the new system are identified.
Coherent
[6 empty] | The requirements are captured and shared with the team and the stakeholders. | the big picture is clear and shared by all involved
[6 empty] | The most important usage scenarios for the system can be explained. | important usage scenarios explained
[6 empty] | The priority of the requirements is clear. | priorities are clear
[6 empty] | Conflicting requirements are identified and attended to. | conflicts are addressed
[6 empty] | The impact of implementing the requirements is understood. | impact is understood
The origin of the requirements is clear.
The requirements communicate the essential characteristics of the system to be delivered.
The rationale behind the requirements is clear.
The team understands what has to be delivered and agrees to deliver it.
Acceptable
[6 empty] | The stakeholders accept that the requirements describe an acceptable solution. | requirements describe a solution acceptable to the stakeholders
[6 empty] | The rate of change to the agreed requirements is relatively low and under control. | the rate of change to agreed requirements is low
[6 empty] | The value provided by implementing the requirements is clear. | value is clear
The parts of the opportunity satisfied by the requirements are clear.
The requirements are testable
Addressed
[6 empty] | Enough of the requirements are addressed for the resulting system to be acceptable to the stakeholders. | enough requirements are implemented for the system to be acceptable
[6 empty] | The system implementing the requirements is accepted by the stakeholders as worth making operational. | stakeholders agree the system is worth making operational
The stakeholders accept the requirements as accurately reflecting what the system does and does not do.
The set of requirement items implemented provide clear value to the stakeholders.
Fulfilled
[6 empty] | The stakeholders accept the requirements as accurately capturing what they require to fully satisfy the need for a new system. | the system fully satisfies the requirements and the need
[6 empty] | There are no outstanding requirement items preventing the system from being accepted as fully satisfying the requirements. | there are no outstanding requirements items preventing completion
The system is accepted by the stakeholders as fully satisfying the requirements.
Software System | Solution | Yellow | A system made up of software, hardware, and data that provides its primary value by the execution of the software. | A software system can be part of a larger software, hardware, business or social solution.
Architecture Selected
[6 empty] | Architecture selected that address(es) key technical decisions | Architecture selected that address key technical risks
[6 empty] | The criteria to be used when selecting the architecture have been agreed on. | criteria for selecting architecture agreed
[6 empty] | Programming languages and technologies to be used have been selected. | platforms, technologies, languages selected
[6 empty] | Buy, build and reuse decisions have been made. | buy, build, reuse decisions made
Hardware platforms have been identified.
System boundary is known.
Significant decisions about the organization of the system have been made.
Demonstrable
[6 empty] | Key architectural characteristics have been demonstrated. | key architecture characteristics demonstrated
[6 empty] | The relevant stakeholders agree that the demonstrated architecture is appropriate. | relevant stakeholders agree architecture is appropriate
[6 empty] | Critical interfaces have been demonstrated. | critical interface and system configurations exercised
Critical hardware configurations have been demonstrated.
The system can be exercised and its performance can be measured.
The integration with other existing systems has been demonstrated.
Usable
[6 empty] | System is usable and has desired quality characteristics. | system is usable and has desired quality characteristics
[6 empty] | The system can be operated by stakeholders who use it. | system can be operated by users
[6 empty] | The functionality provided by the system has been tested. | functionality and performance have been tested and accepted
[6 empty] | Defect levels are acceptable to the stakeholders. | defect levels acceptable
[6 empty] | Release content is known. | release content known
The performance of the system is acceptable to the stakeholders.
The system is fully documented.
The added value provided by the system is clear.
Ready
[6 empty] | Installation and other user documentation are available. | user documentation available
[6 empty] | The stakeholder representatives accept the system as fit-for-purpose. | stakeholder representatives accept system
[6 empty] | The stakeholder representatives want to make the system operational. | stakeholder representatives want to make system operational
Operational support is in place.
Operational
[6 empty] | System use in operational environment | system in use in operational environment
[6 empty] | The system has been made available to the stakeholders intended to use it. | system available to intended users
[6 empty] | At least one example of the system is fully operational. | at least one example of system is fully operational
[6 empty] | The system is fully supported to the agreed service levels. | system supported to agreed service levels
Retired
[6 empty] | The system is no longer supported. | system no longer supported
[6 empty] | Updates to the system will no longer be produced. | updates to system will no longer be produced
[6 empty] | The system has been replaced or discontinued. | system has been replaced or disnontinued
There are no “official” stakeholders who still use the system.
Team | Endeavor | Blue | The group of people actively engaged in the development, maintenance, delivery and support of a specific software system. | The team plans and performs the work needed to create, update and/or change the software system.
Seeded
[6 empty] | The team mission has been defined (OMG adds: "in terms of the opportunities and outcomes"). | team's mission is clear
[6 empty] | Mechanisms to grow the team are in place. | team knows how to grow to achieve mission
[6 empty] | Required competencies are identified. | required competencies are identifed
[6 empty] | The team size is determined. | team size is determined
Constraints on the team's operation are known.
The composition of the team is defined.
Any constraints on where and how the work is carried out are defined.
The team's responsibilities are outlined.
The level of team commitment is clear.
Governance rules are defined.
Leadership model is selected.
Formed
[6 empty] | Team has enough ressources to start the mission | team has enough resources to start the mission
[6 empty] | Every team member understands how the team is organized and what their individual role is. Individual responsibilities are understood. | team organization & individual responsibilities understood
[6 empty] | All team members understand how to perform their work. | members know how to perform work
Enough team members have been recruited to enable the work to progress.
The team members have met (perhaps virtually) and are beginning to get to know each other
The team members understand their responsibilities and how they align with their competencies.
Team members are accepting work.
Any external collaborators (organizations, teams and individuals) are identified.
Team communication mechanisms have been defined.
Each team member commits to working on the team as defined.
Collaborating
[6 empty] | The team is working as one cohesive unit. | members working as one unit
[6 empty] | Communication within the team is open and honest. | communication is open and honest
[6 empty] | The team is focused on achieving the team mission. | members focused on team mission
[6 empty] | Success of team ahead of personal objectives. | success of team ahead of personal objectives
The team members know each other.
Performing
[6 empty] | The team consistently meets its commitments. (OMG version: "Team working efficiently and effectively") | team working efficiently and effectively
[6 empty] | The team continuously adapts to the changing context. | adapts to changing context
[6 empty] | Produce high quality output | produce high-quality output
[6 empty] | Effective progress is being achieved with minimal avoidable backtracking and reworking. | mininal backtracking and re-work
[6 empty] | Wasted work, and the potential for wasted work are continuously eliminated. | waste continually eliminated
The team identifies and addresses problems without outside help.
Adjourned
[6 empty] | Team no longer accoutable (OMG version: "The team responsibilities have been handed over or fulfilled.") | team no longer accountable
[6 empty] | Responsibilities handed over | responsibilites handed over
[6 empty] | The team members are available for assignment to other teams. | members available for other assignment
No further effort is being put in by the team to complete the mission.
Way-of-Working | Endeavor | Blue | The tailored set of practices and tools used by a team to guide and support their work. | The team evolves their way of working alongside their understanding of their mission and their working environment. As their work proceeds they continually reflect on their way of working and adapt it to their current context, if necessary. |  |  | THE STRIP REFLECTS A VERY UPFRONT VIEW OF SELECTING TOOLS & PRACTICES...
[5 empty] | Principles Established |  | The term principle is a bit vague. This state could be called "Agreed" ???
[6 empty] | Principles and constraints established | principles and constraints established
[6 empty] | Principles and constraints are committed to by the team. | principles and constraints comitted to
[6 empty] | Practices and tools agreed to | practices and tools agreed to
[6 empty] | The context within which the team will operate is understood. | context team operates in understood
Principles and constraints are agreed to by the stakeholders.
The tool needs of the work and its stakeholders are agreed.
A recommendation for the approach to be taken is available.
The constraints that apply to the selection, acquisition and use of practices and tools are known.
[5 empty] | Foundation Established |  | The term foundation is a bit vague. This state could be called "In Place" or "Ready" ???
[6 empty] | Key practices and tools ready | key practices and tools ready
[6 empty] | The gaps that exist between the practices and tools that are needed and the practices and tools that are available have been analyzed and understood. | gaps that exist between practices and tools analyzed and understood
[6 empty] | The capability gaps that exist between what is needed to execute the desired way of working and the capability levels of the team have been analyzed and understood. | capability gaps analyzed and understood
[6 empty] | The selected practices and tools have been integrated to form a usable way-of-working. | selected practices, and tools integreated
The key practices and tools that form the foundation of the way-of-working are selected.
Enough practices for work to start are agreed to by the team.
All non-negotiable practices and tools have been identified.
In Use
[6 empty] | Some members of the team are using the way of working (OMG version: "The practices and tools are being used to do real work.") | some members of the team are using the way of working
[6 empty] | The use of the practices and tools selected are regularly inspected. | use of practices and tools regularly inspected
[6 empty] | The practices and tools are being adapted to the team’s context. The use of the practices and tools is supported by the team. | practices and tools being adapted and supported by the team
[6 empty] | Procedures are in place to handle feedback on the team’s way of working. | procedures in place to handle feedback
The practices and tools support team communication and collaboration.
In Place
[6 empty] | The practices and tools are being used by the whole team to perform their work. | all members of the team are using the way of working
[6 empty] | All team members have access to the practices and tools required to do their work. | all members have access to the practices and tools to do their work
[6 empty] | The whole team is involved in the inspection and adaptation of the way-of-working. | whole team involved in inspections and adaptation of way of working
Working well
[6 empty] | The way of working is working well for team | way of working is working well for team
[6 empty] | Team members are making progress as planned (OMG adds: "by using and adapting the way-of-working to suit their current context.") | team memers are making progress as planned
[6 empty] | The team naturally applies the practices without thinking about them | team naturally applies practices withouth thinking about them
[6 empty] | The tools naturally support the way that the team works. | tools naturally support the way of working
The team continually tunes their use of the practices and tools.
Retired
[6 empty] | The team's way of working is no longer being used. | way of working no longer in use by team
[6 empty] | Lessons learned are shared for future use. | lessons learned are shared for future use
Work | Endeavor | Blue | Activity involving mental or physical effort done in order to achieve a result. | In the context of software engineering, work is everything that the team does to meet the goals of producing a software system matching the requirement and addressing the opportunity presented by the stakeholders. The work is guided by the practices that make up the team’s way-of-working.
Initiated
[6 empty] | The initiator of the work is clearly identified. | work initiator known
[6 empty] | Any constraints on the work’s performance are clearly identified. | work constraints clear
[6 empty] | The stakeholders that will fund the work are known. The source of funding is clear. | sponsorship and funding model clear
[6 empty] | The priority of the work is clear. | priority of work clear
The result required of the work being initiated is clear.
The stakeholders that will accept the results are known.
Prepared
[6 empty] | Cost and effort of the work are estimated. | cost & effort estimated
[6 empty] | Funding (Srtip: and ressources) to start the work is in place. | funding and resources to start work in place
[6 empty] | Acceptance criteria are defined (OMG adds: "and agreed with client.") | acceptable criteria understood
[6 empty] | Governance (OMG adds: "policies and") procedures are clear. | governance procedures agreed
[6 empty] | Risk exposure is understood. | risk exposure understood
[6 empty] | Dependencies are clear. | dependencies clear
Commitment is made.
Resource availability is understood.
The work is broken down sufficiently for productive work to start.
Tasks have been identified and prioritized by the team and stakeholders.
A credible plan is in place.
Started
[6 empty] | Development work has been started. | development work has started
[6 empty] | Work progress is monitored. | work progress is monitored
[6 empty] | The work is being broken down into actionable work items with clear definitions of done. | work broken down into actionable items with clear definition of done
[6 empty] | Team members are accepting and progressing tasks. | team members accepting and progressing work items
Under Control
[6 empty] | Work going well, risks being managed | work going well, risks being managed
[6 empty] | Unplanned work & re-work under control. | uplanned work & re-work under control
[6 empty] | Tasks are being completed. Tasks are consistently completed on time and within their estimates. | work items completed with estimates
[6 empty] | Measures tracked (OMG version: "Measures are available to show progress and velocity.") | measures tracked
Risks are under control as the impact if they occur and the likelihood of them occurring have been reduced to acceptable levels.
Estimates are revised to reflect the team’s performance.
Concluded
[6 empty] | Work to produce results have been finished (OMG version: "All outstanding tasks are administrative housekeeping or related to preparing the next piece of work.") | work to produce results have been finished
[6 empty] | Work results have been achieved. | work results are being achieved
[6 empty] | The stakeholder(s) has accepted the resulting software system. | the client has accepted the resulting software system
Closed
[6 empty] | All remaining housekeeping tasks completed, and work officially closed. | all remaining housekeeping tasks completed, and work officially closed
[6 empty] | Everything has been archived. | everything has been archived
[6 empty] | (OMG: Lessond learned and) metrics have been made available. | lessons learned and metrics made available
Lessons learned have been itemized, recorded and discussed.
The budget has been reconciled and closed.
The team has been released.
There are no outstanding, uncompleted tasks.