## Mapping
Alpha | Concern | Color | Definition | Description | Card | Checklist
Stakeholders | Customer | Green | The people, groups, or organizations who affect or are affected by a software system. | The stakeholders provide the opportunity, and are the source of the requirements for the software system. They are involved throughout the software engineering endeavor to support the team and ensure that an acceptable software system is produced.
Recognized
Possible stakeholders groups are identified
Team agrees on relevant stakeholder groups to be represented
Responsibilities of stakeholder representatives are defined
Represented
Stakeholder representatives are appointed
Stakeholder representatives agree to take on responsibilities
Stakeholders agree on collaboration approach
Representatives respect team's way of working
Stakeholder representatives empowered to take on responsibilities
Involved
Stakeholder representatives carry out responsibilities
Stakeholder representatives provide feedback & take part in decisions in timely way
Stakeholder representatives promptly communicate to stakeholder group
In Agreement
Team values stakeholder representatives' input
Stakeholder representatives agree with priorities
Stakeholder representatives agreed upon minimal expectations for deployment
Stakeholder representatives value team's input
Satisfied for Deployment
Stakeholder representatives confirm system ready for deployment
Experimenting
Stakeholders provide feedback on their experiences with the deployed system
Satisfied in Use
Stakeholders confirm that system meets their expectations.
Opportunity | Customer | Green | The set of circumstances that makes it appropriate to develop or change a software system. | The opportunity articulates the reason for the creation of the new, or changed, software system. It represents the team’s shared understanding of the stakeholders’ needs, and helps shape the requirements for the new software system by providing justification for its development.
Identified
Software-based solution addresses an identified opportunity
Stakeholders wish to make an investment in better understanding potential value
Solution Needed
Problem is clearly articulated
Opportunity addresses problem and stakeholder needs.
Software can solve the problem.
Value Established
Projected value of software system established
Impact of solution on stakeholders understood
Success criteria are clear
Desired outcomes are clear
Viable
Solution has been outlined
Solution is deployable within constraints
Risks associated with solution are acceptable and manageable.
Addressed
Solution demonstrably addresses opportunity
A usable system is available
Solution is worth deploying
Benefit Accrued
Operational use of solution creates tangible benefits
Return on investment is acceptable
Requirements | Solution | Yellow | This area of concern covers everything to do with the specification and development of the software system. | The goal of software engineering is to develop working software as part of the solution to some problem. Any method adopted must describe a set of practices to help the team produce good quality software in a productive and collaborative fashion.
Conceived
List of high-level requirements captures system purpose
User types are identified
Bounded
Purpose and extent of system are agreed
Success criteria are clear
Processes and tools for handling requirements are in place
Scope constraints are identified
Assumptions made while defining requirements are captured
Coherent
Requirements are captured and shared
Important usage scenarios are explained
Requirements are prioritized
There are no conflicting requirements
Rationale and impact are understood
Acceptable
Requirements are acceptable to stakeholders
Rate of change is acceptable
Value is clear
Requirements are testable
Addressed
Core requirements are implemented
Stakeholders agree implemented requirements are worth making operational
Fulfilled
There are no outstanding requirements to be implemented
Implemented requirements satisfy the need for a new system
Implemented requirements are fully accepted
Software System | Solution | Yellow | A system made up of software, hardware, and data that provides its primary value by the execution of the software. | A software system can be part of a larger software, hardware, business or social solution.
Initiated
Criteria for selecting architecture are agreed
Platforms, technologies, languages are selected
Selected architecture addresses key technical risks
Buy, build, reuse decisions are made
Stakeholders agree on necessary documentation
Stakeholders agree on support service levels
Demonstrable
Key architecture characteristics are demonstrated
Relevant stakeholders agree architecture is appropriate
Critical interfaces and system configurations demonstrated
Usable
Users can operate system
System has desired quality and performance characteristics
Functionality is tested and accepted
Defect levels are acceptable
Ready
Agreed documentation is available
Stakeholder representatives accept system
Operational
System is in use in operational environment
System is available to intended users
System is supported to agreed service levels
Maintained
New requirements are accommodated
System is updated to newer technologies or platforms
Issues and bugs are tracked and resolved
Design is improved
Service support levels are monitored
Retired
System is replaced or no longer supported
Team | Endeavor | Blue | The group of people actively engaged in the development, maintenance, delivery and support of a specific software system. | The team plans and performs the work needed to create, update and/or change the software system.
Seeded
Team's mission is clear
Team can grow to achieve opportunity
Required skills are identified
Target team size is determined
Where and how the work is carried out are defined
Responsibilities and roles are outlined
Decision making processes are decided
Formed
Team has enough resources to start addressing opportunity
Team organization, responsibilities, and roles are understood
Members know how to perform their work
External collaborators are identified
Collaborating
Members are working as one unit
Communication is open and professional
Members are focused on opportunity
Team's objectives are aligned with personal objectives
Performing
Team consistently meets its commitments
Team adapts to change
Team overcomes challenges
Team produces high-quality output
Team strives to eliminate waste
Adjourned
Team is no longer accountable
Way-of-Working | Endeavor | Blue | The tailored set of practices and tools used by a team to guide and support their work. | The team evolves their way of working alongside their understanding of their mission and their working environment. As their work proceeds they continually reflect on their way of working and adapt it to their current context, if necessary.
Values and Principles Established
Values and principles are identified
Team commits to values and principles
Stakeholders accept team's values and principles
Practices & Tools Selected
Constraints about practices and tools are known
Practices and tools are identified to address team's needs
Practices and tools are consistent with values and principles
A transition plan is defined to adopt new practices and tools
Stakeholders accept external-facing practices & tools
In Use
Practices and tools are ready
Team is adopting practices, tools, principles, and values
Team reflects on practices, tools, principles, and values
Team is adapting practices and tools
Working well
Team naturally applies practices and tools
Practices and tools naturally support team
Team continues to tune practices and tools
Team fully embraces principles and values
Retired
Team captures lessons learned
Work | Endeavor | Blue | Activity involving mental or physical effort done in order to achieve a result. | In the context of software engineering, work is everything that the team does to meet the goals of producing a software system matching the requirement and addressing the opportunity presented by the stakeholders. The work is guided by the practices that make up the team’s way-of-working.
Initiated
Work initiator is known
Work constraints are known
Funding model is clear
Importance of work is clear
Prepared
Cost and effort are estimated
Resources to start work are in place
Acceptance criteria are defined
Oversight is in place
Rules and regulations are understood
Risk exposure is understood
Commitment is made
A credible plan is in place
Started
Work is broken down into actionable items with clear definitions of done
Team members are progressing on work items
Progress metrics are identified
Progress is monitored
Under Control
Work items are being completed at a steady pace
Unplanned work is manageable
Rework is manageable
Progress metrics are tracked and acted upon
Risks are managed
Plan is revised to reflect team's performance
Concluded
All work items are completed
Stakeholders are satisfied with results
Closed
Any housekeeping tasks are completed
Work artifacts are archived
Progress metrics are archived
Actual cost and effort recorded